## Sheet1
No. | Task Descriptions | Duration (month) | Timeframe
1 | Perform literature review | 1 | Aug. 2020
2 | #1 - Investigate the current distribution of PV and EV | 1 | Sep. 2020
3 | #1 - Find the relationships between EV, PV and features | 1 | Oct. 2020
4 | #1 - Validate the social equity with the diffusion patterns | 1 | Nov. 2020
5 | #2 - Aggregate data for the spatio-temporal analyses | 1 | Dec. 2020
6 | #2 - Identify peer effects on diffusion trends | 1 | Jan. 2021
7 | #2 - Investigate diffusion methods to explain peer effects | 1 | Feb. 2021
8 | #3 - Integrate PV and EV to investigate reliability impact | 1 | Mar. 2021
9 | #3 - Construct a model to identify vulnerable communities | 1 | Apr. 2021
10 | #3 - Validate the model in case studies | 1 | May. 2021
11 | Prepare the dissertation | 2 | Jun. - Jul. 2021
12 | Total | 12 | Aug. 2020 - Jul. 2021